| HMICFRS Area for Improvement – Sign off and closure report |  |  |  |
| --- | --- | --- | --- |
| Area for improvement |  | Protecting the public through fire regulation |  |
| Pillar |  | Protection |  |
| Strategic Lead |  | Lee Brown |  |
| Project Lead |  | Lee Haggath |  |
| Area for Improvement action detail |  |  |  |
| AFI Ref: No 6 - The brigade should make sure it works with local businesses and other organisations to share information and expectations on compliance with fire safety regulations |  |  |  |
| What has been completed? (Summary of actions undertaken to deliver improvement) |  |  |  |
| The Brigade has undertaken a comprehensive programme of business engagement activity designed to strengthen how it communicates with local businesses and responsible persons, in direct response to the HMICFRS Area for Improvement (AFI) relating to sharing information and expectations on compliance with fire safety regulations. This work has been delivered through a structured Business Fire Safety Engagement Plan, which spans proactive communication, targeted education, and sustained partnership working across the four local authority areas. The programme reflects a clear strategic intention to move beyond one-way communication and instead create meaningful, two-way engagement with business sectors, ensuring responsible persons are better informed, more capable, and increasingly compliant with their duties under the Regulatory Reform (Fire Safety) Order 2005. Throughout the year, the Protection Department plans to adopt a blended communication model to Business Engagement and educating the business’ in our area through a combination of face-to-face seminars, virtual sessions, digital campaigns, post-incident engagement, and consistent use of recognised platforms such as the brigade website and social media channels. An extensive annual campaign calendar has also been implemented, aligned closely to NFCC national campaigns, and supplemented by local priorities identified in the brigade’s CRMP and audit findings. This has been uploaded to the Protection Department SharePoint site (Business Engagement) and will be uploaded to the staff facing side to the site. This can also then be uploaded to any public facing side of our website Regular messaging will be shared on electrical safety, smoke detection responsibilities, fire door safety, escape routes, seasonal risks, and specialist themes such as dementia awareness and student fire safety. Each campaign is designed to be accessible, timely, and supported by approved guidance and resources hosted through the brigade’s forward-facing website. This ensures consistency, high visibility, and a clear audit trail of sustained engagement activity. This messaging will take place across various platforms such as LinkedIn, Facebook, X and the Brigade’s external facing website. The brigade has also strengthened its post-incident engagement processes. Following commercial fires, direct liaison with affected businesses is undertaken to provide bespoke guidance, reinforce compliance standards, and address findings identified through post fire investigations (SPFI). Where non-compliance is found to have contributed to a fire, the brigade ensures proportionate enforcement action is taken in line with the Regulators’ Code, increasing transparency and accountability. This takes the form of a Fire Safety Audit following the SPFI where all actions are subsequently recorded on CFRMIS against the relevant premises ID and followed up as per the current procedure following a Fire Safety Audit This approach creates valuable opportunities to share lessons, raise awareness, and prevent recurrence, while reinforcing expectations around duty-holder responsibilities |  |  |  |
| Delivery outcomes (What are the success factors) |  |  |  |
| - Improved understanding of fire safety duties among responsible persons, demonstrated through increased enquiries, seminar attendance and use of online guidance resources. - Strengthened relationships with local business sectors, including care settings, education providers, hospitality, and retail, enabling more responsive and tailored regulatory support. - Greater consistency and reach of fire safety messages, due to coordinated digital engagement aligned to the NFCC campaign calendar. - Reduction in repeat non-compliance themes, supported by targeted communications directly addressing issues identified through audits and post-incident investigations. - Enhanced transparency and accountability, achieved through clear communication of expectations, enforcement principles and post-incident learning. - A demonstrable shift toward proactive compliance, supported by improved access to templates, guidance, and self-help tools through the brigade’s website. Business’ will also be able to provide feedback on a brief online questionnaire (Microsoft Forms). |  |  |  |
| Follow on actions? (Action to be detailed with target dates and owners identified) |  |  |  |
| Action | Owner |  | Target date |
| 12 month review on the number of Business Engagement events being recorded on CFRMIS by the BFSA’s. Success will see an increase in the number of business engagement activities recorded on the CFRMIS system by the BFSA’s | Michael Smith |  | 31/04/2027 |
| Supporting Evidence - documents/links |  |  |  |
| Business Engagement |  |  |  |
| Lessons learnt |  |  |  |
| CFB did not use the full suite of tools available to it for Business Engagement. Such as digital platforms and Fire Safety Interventions. Engagement can come in many forms and should be captured as such on the CFRMIS system with a new code being implemented to record all business safety engagements making them readily reportable. |  |  |  |

| Current level of assurance | Substantial |
| --- | --- |
| Sign off and closure confirmed | Yes |
| Directorate sign off | Yes |
| Date | 29th April 2026 |
| Executive Leadership Team sign off | Agreed |
| Date | 5th May 2026 |

| Version Control – Governance and Assurance only |  |  |
| --- | --- | --- |
| Version No. | Name | Date |
| 0.1 | Nicola Tranter | November 2025 |