## CLF
Project | Report Title | Recommendation Monipotal Number (Hidden column for Admin only) | Recommendation description | Due date | Service Update Summary | Is this recommendation complete? | Date Completed
Cleveland FRS | Values and culture in fire and rescue services | 27130 (Rec 34) | With immediate effect, chief fire officers should review their implementation of the Core Code of Ethics [https://www.firestandards.org/standards/approved/code-of-ethics-fsc-eth01/] and make sure it is being applied across their services. | 2023-03-30 | Following the publication of the Fire Standard 'Code of Ethics' in May 2021, we undertook a gap analysis to help us identify any areas for improvement. The outcome from this work, was minor amendments to our existing Values and Behaviours Framework and Employee’s Code of Conduct. Together these set out the standards that uphold our organisational culture. HMICFRS Inspection 2021/22 Page 37: ‘CFB is good at promoting its values and culture ..... Brigade values are established, and its culture continues to improve’. To further embed our values and ethical behaviours over the last three years we have: • embedded them into our recruitment, selection, and promotion arrangements • enhanced our induction process to ensure that new employees and newly promoted members of staff are fully aware of their values and behaviours and associated responsibilities • better aligned our learning and development arrangements to the framework through annual e-learning and Personal Development Review processes • improved our procurement arrangements by mainstreaming equality considerations We were assessed as 'good' by HMICFRS Inspection team in relation to this area. Staff survey findings within the inspection show that over 92% of respondents agreed that line managers and colleagues consistently demonstrate the Brigade’s values. HMICFRS acknowledged that the Brigade had carried out an analysis of our values to implement the new national Core Code of Ethics confirming this work had been completed and that the Brigade values were aligned to the National Code. In addition, 79% of survey respondents agreed that senior leaders consistently modelled the Brigade’s values. Moreover, it was found that staff were empowered and willing to challenge poor behaviours. HMICFRS 20221/22 Page 37. | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 26628 (Rec 17) | With immediate effect, chief fire officers should notify HMICFRS of any allegations that have the potential to constitute staff gross misconduct that: - involve allegations of a criminal nature that have the potential to affect public confidence in FRSs; - are of a serious nature; or - relate to assistant chief fire officers or those at equivalent or higher grades. | 2023-03-30 | On receipt of request in February we have been sending monthly information to the HMICFRS re. staff gross misconduct and we have put a system in place to ensure we update this information monthly moving forward. The Brigade's Discipline and Grievance policies have been updated to reflect the responsibilities of the Chief Fire Officer and to formalise the system for reporting allegations that have the potential to constitute staff gross misconduct. On 19th July 2023, HMI Wilshire advised that the returns were to be sent to HMI Michelle Skeer with immediate effect. He also went on to thanks us for keeping him updated on the disciplines and related issues in a 'regular and comprehensive manner'. | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 27040 (Rec 32) | Chief Fire Officers should, as a priority, specify in succession plans how they intend to improve diversity across all levels of the service. This should include offering increased direct-entry opportunities | 2023-06-01 | CFB has a Workforce Plan and a Succession Plan in place which covers our intentions relating to improving skills, capabilities, and the diversity of our workforce across all levels - this was acknowledge by HMICFRS 2021/22 Page 40. The well-embedded workforce and succession planning arrangements are strategically led by the Executive Leadership Team. On going projects to support the diversification of our workforce include: • new approach to positive action (core work) • development of a CFB recruitment brand (Project PPP15.1) • identifying barriers to the recruitment and retention of staff to under-represented groups (Project PPP14.2) • explore Direct Entry as a means of recruiting to senior positions (Project PPP16) • undertake a gap analysis of our recruitment arrangements against NFCC Recruitment Maturity Model Level 4 (Project PPP25.2) Our 'Integrated Talent Management Framework' includes opportunity for staff to be developed beyond role. The Development Gateway seeks to provide all staff, regardless of role and level, with the opportunity to reach their potential and be the best they can be. Following a pilot, a full roll out of the Gateway commenced in Apr 2023. | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | (Rec 27) | By 1st June 2023, Chief Fire Officers should make sure their equality impact assessments are fit for purpose and, as a minimum, meet the requirements of the NFCC Equality Impact Assessment Toolkit | 2023-06-01 | EQIA’s are a requirement in the development of all CFB policies and our processes are well -embedded and aligned to the NFCC EQIA toolkit. HMICFRS 2021/22 (Page 44) CFB has an effective process in place to assess equality impact. Our inspection found a comprehensive approach to equality impact assessments and people impact assessment with all published policies and procedures having assessments in date and completed. | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 26390 (Rec 4) | Chief Fire Officers should assure themselves that updates on how concerns are being handled are shared with those who have raised them. The updates should be given in an accessible way that encourages trust and confidence in the service response. Consideration should be given to creating professional standards function to handle conduct concerns in service (or from an external service) to have oversight of cases, to make sure they are conducted in a fair and transparent way and to act as a point of contact for all staff involved. | 2023-06-01 | Our feedback arrangements have been clarified within our review of our Whistleblowing, Dignity at Work, and Grievance policies. The internal HR team carries out the ‘professional standards function’ for the Brigade. This includes the appointment of a HR professional to each case who ensures that the process is carried out in line with policy and is applied consistently. This person is the single point of contact for the case and is responsible for ensuring that the individual raising the concern is regularly updated on progress. We are conisdering enhancing our current arrangements and have commenced a project to explore our options. Given the work and research required to successfully carry out this project a sensible completion date is Mar 2024. | YES | 2023-12-03
Cleveland FRS | Values and culture in fire and rescue services | 26992 (Rec 28) | By 1 June 2023, chief fire officers should review how they gather and use equality and diversity data to improve their understanding of their staff demographics, including applying and meeting the requirements of the National Fire Chiefs Council equality, diversity and inclusion data toolkit [https://www.ukfrs.com/equality-diversity-and-inclusion-data-toolkit]. | 2023-06-01 | We have an accessible digital platform relating to the diversity profile of our workforce and community – Project PPP7.1. These profiles are based on the most current publicly available sources of data. The workforce data is aligned to the protected characteristics (Equalities Act 2010). The profile can be analysed by duty system and role. Temporal analysis provides crucial insight on trends. The data within the Community Profile is aligned to the protected characteristics and is sourced from ONS. The profile can be analysed at Brigade, District and Ward level with the ability to analyse at a more granular level if required. Our interactive toolkit allows us to compare workforce diversity against community diversity and supports the targeting of community safety initiatives, engagement with hard-to-reach groups and positive action recruitment. Other sources of EDI community data are obtained from partners and users of our services. For staff these include grievances, disciplines, staff turnover, and promotions.All data collected and published by the Brigade is compliant with the Data Protection Act 2018. Monitoring of performance is well embedded and Audit & Governance and Executive Leadership Team receive regular reports on progress against EDI indicators. Reports are widely published on the Brigade’s website and Intranet. EDI performance is regularly communicated with staff. Project PPP6.1 reviewed existing performance indicators providing more focussed measurements against the strategic outcomes for EDI. As a result of this work our existing suite of indicators were expanded in Apr 2023 and these will be evaluated after first year (PPP 6.2). We have for many years, in line with our statutory duty, published a PSED and Gender Pay Gap Reports. In addition, we have voluntary reported on Disability, Mental Health and Wellbeing and Ethnicity Pay Gap. EQIA’s are a requirement in the development of all CFB policies and our processes are well -embedded. | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 26854 (Rec 23) | By 1 June 2023, chief fire officers should seek regular feedback from staff about values, culture, fairness and diversity, with due regard to the leading and developing people standard [https://www.firestandards.org/standards/approved/leading-developing-people-fsc-led01a/]. They should show how they act on this feedback. | 2023-06-01 | Our Corporate Plans were developed following extensive consultation with staff and TUs; encouraging buy-in and consensus to the Authority’s strategic direction. Our embedded Meetings and Decision-Making Framework gives opportunity for feedback at all levels. The HWB, H&S and EDI Boards are forums where staff meet with senior managers and TUs to drive strategies and discuss areas of concern e.g., values and ethical behaviours, cause for concerns. We have good industrial relations working constructively with TUs to support our people. Facilities time is provided. At tactical level, ERG deals with operational issues; issues that cannot be resolved are fed into strategic level. Our Recruitment and Selection Policy, developed through staff engagement, embeds our values and behaviours; providing applicants’ opportunities to receive feedback at each stage. Candidates concerned over any aspect of the process are directed to the Grievance Policy. Our Grievance, Dignity at Work and Discipline Policies provide opportunity for staff to receive feedback and offer the right of appeal against any decision made. Our Staff engagement strategy includes: • Principal Officers visit stations/departments to engage and seek staff feedback • Leadership events provide opportunity for leaders to network, develop and exchange views on topical matters. • Staff Networks (Women, Disability, Cultural Diversity, LGBT+) provide opportunities for staff to express views on matters through the EDI Board. • Weekly Staff Communications Forum provides opportunity for two-way feedback with POs • Undertake Staff Surveys to gain feedback on specific topics e.g., ICT training needs • Staff Suggestion Scheme allows staff to submit suggestions for service improvements and includes a feedback mechanism. PDRs including wellbeing conversations ensure that managers speak to staff regularly and facilitate discussions on areas of concern.We undertake exit interviews to gain information relating to all aspects of the work environment which is analysed to establish trends. Immediate resolutions are actioned for areas of concern. | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 26764 (Rec 21) | By 1 June 2023, chief fire officers should make sure there is a full, 360-degree feedback process in place for all senior leaders and managers (assistant chief fire officer equivalent and above) in service. (Rec 21) | 2023-06-01 | We have a project in place (PPP 35.1) to explore and introduce 360-degree feedback for all managers within CFB and the project runs from Apr 2023 - Mar 2024. We are currently considering how 360 feedback will link into our existing leadership development arrangements. We have engaged with an NFCC recommended supplier fro the introduction of 360 appraisals into the Brigade and we are currently entering the procurement process. | In progress
Cleveland FRS | Values and culture in fire and rescue services | (Rec 22) | Chief Fire Officers should make sure that there is a full, 360-degree feedback process in place for all other leaders and managers in the service. The process should include gathering feedback from a wide range of sources including colleagues and direct reports | 2023-09-01 | We have a project in place (PPP 35.1) to explore and introduce 360-degree feedback for all managers within CFB and the project runs from Apr 2023 - Mar 2024. We are currently considering how 360 feedback will link into our existing leadership development arrangements. We have engaged with an NFCC recommended supplier fro the introduction of 360 appraisals into the Brigade and we are currently entering the procurement process. | In progress
Cleveland FRS | Values and culture in fire and rescue services | 26719 (Rec 20) | By 1 June 2023, chief fire officers should have plans in place to ensure they meet the "Fire Standards Boards leading the service standard"[https://www.firestandards.org/standards/approved/leading-the-service-fsc-led01b/] and its "leading and developing people standard" [https://www.firestandards.org/standards/approved/leading-developing-people-fsc-led01a/]. | 2023-06-01 | A comprehensive gap analysis has been undertaken against the 'Leading the Service' Fre Standard. and approved by ELT. In the main, our approach to leading the service is fully compliant with the standard - two sub areas are partially compliant and these relate to use of technology and data literacy. We already have plans in place to adress these and therefore no new improvement actiion plan is required. The ‘Gap Analysis’ relating to the Leading and Developing People Fire Standard are scheduled for completion to the Internal Fire Standards Board in Mar 2024. Following on from here an action plan will be produced to address any agreed gaps | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 26435 (Rec 5) | By 1 June 2023, chief fire officers should make sure they provide accessible information for all staff and members of the public on how they can raise concerns and access confidential support (including through external agencies). Chief fire officers should also make sure accessible information is provided on how concerns and allegations will be investigated in a way that ensures confidentiality and is independent of the alleged perpetrator. | 2023-06-01 | Our external website, independently assessed as being ‘accessibility compliant’ gives access to people with visual impairment or people where English in not their first language. The landing page of our external website gives quick access for members of the public to raise a concern about a member of staff or service. Easy to follow instructions are provided on how to make a complaint via the most suitable mechanism e.g., website, telephone, email, in writing or in person. The instructions set out the expectations and timescales for completion of each stage of the complaints process and provide a link to the Local Government Ombudsman should the complainant be dissatisfied with the outcome or how the complaint was handled. The public are provided with similar guidance on how to make a complaint against an Elected Member of the Fire Authority. Our ‘whistleblowing’ policy is available on the website. We continuously analyse complaints from the public through ELT as part of our performance management arrangements. This helps to identify trends and areas for improvement. The Dignity at Work, Grievance and Whistleblowing policies are always accessible for staff to raise a concern via the Brigade’s intranet site. They set out details of the process including how confidentiality and independence will be assured and the expectations and timelines associated with every stage. Our key systems such as H&S Reporting and Occupational Health Referral allow staff to report any concerns relating to individual health, safety and wellbeing. The EAP and other services such as counselling, Samaritans, and MIND are signposted throughout the Brigade on various noticeboards. Our face-to-face communications further facilitates staff to raise concerns; these include: Principal Officers visits;Line Managers; PDRs including wellbeing conversations;Peers Staff Networks (Women, Disability, Cultural Diversity, LGBT+);Mental Health Champions;TRIMS Assessors;Buddies;Staff Surveys;Exit Interviews;Trade Unions | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 26345 (Rec 3) | By 1 June 2023, chief fire officers should review the support available for those who have raised concerns and take any action needed to make sure these provisions are suitable. | 2023-06-01 | Our Whistleblowing, Grievance and Dignity at Work policies and procedures all signpost individuals to sources of support and advice for those staff who have raised a concern; these being where appropriate the appointment of a welfare officer, signposting to professional help (e.g. Brigade's Occupational Health and/or Counselling Services), formalising a system for maintaining communications, re-locating workplace of either party and offering mediation. | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 27085 (Rec 33) | By 1 August 2023, chief fire officers should develop plans to promote progression paths for existing staff in non-operational roles and put plans in place to reduce any inequalities of opportunity. | 2023-08-01 | As confirmed by HMICFRS 2021/22 Pages 45 and 46 we have processes for promotion and progression that are fair, comprehensive, understood by staff and cover opportunities in all roles. We have improved at identifying, developing, and supporting talent and leadership skills at all levels. Our integrated Talent Management Framework includes opportunity for staff to be developed beyond role. The Development Gateway seeks to provide all staff, regardless of role and level, with the opportunity to reach their potential and be the best they can be. Following a pilot, a full roll out of the Gateway commenced in Apr 2023. | YES | 2023-03-31
Cleveland FRS | Values and culture in fire and rescue services | 26673 (Rec 18) | By 1 August 2023, chief fire officers should provide assurances to HMICFRS that all parties are supported in relation to ongoing investigations. | 2023-08-01 | For individuals making allegations against another individual and for individuals under investigation we would appoint a welfare officer, signpost to professional help (e.g. Brigade's Occupational Health and/or Counselling Services), formalise a system for maintaining communications, re-locating workplace of either party and offer mediation. Support for individuals carrying out the investigation/hearing includes: appropriate training in investigation and hearing manager responsibilities, the appointment of an HR case advisor re process, and signposting to professional help (e.g. Brigade's Occupational Health and/or Counselling services) (Letter sent to HMICFRS dated 21st June 2023). | YES | 2023-06-21
Cleveland FRS | Values and culture in fire and rescue services | 26945 (Rec 26) | By 1 October 2023, as a precursor to the development of the College of Fire and Rescue, chief fire officers and the National Fire Chiefs Council should work with the Home Office to consider how they can improve the training and support they offer to staff in management and leadership development. This should include authority members in respect of their assurance leadership roles and should ensure that opportunities are offered fairly across all staff groups. | 2023-10-01 | CFB has aligned the development of leaders in all roles and at all levels to the NFCC Leadership Model and Core Learning Pathway. This includes delivery of leadership and managements qualifications using the Apprenticeship Framework and people modules such as health, safety, and wellbeing, challenging inappropriate behaviours and equality, diversity, and inclusion. CFB has access to the NFCC Coaching network portal. Currently we are building into the training need analysis 2024/25 a financial bid to procure coaching training from an external provider. We have made enquiries with London Fire Brigade who NFCC state are a good example of introducing coaching into the service. They have offered us to free places on their next course for ‘train the trainer’ coaching. Once we have some CFB staff trained as coaches and on the national register, we will communicate this out to staff as part of their leadership development/on promotion/gateway applicants. We invest in leadership development through our staff conference events which to date have focussed on leadership, EDI and Health and Wellbeing. Our 2023/24 programme of events includes a health and wellbeing conference (EDI 1.2) scheduled for Feb 2024 the outcomes from which will contribute to 'Making CFB a Great Place to Work'. Member development is mostly undertaken within Members’ constituent councils. Specific training is provided on issues relating to the Fire Authority e.g., values and behaviour and code of ethics. Elected member development is aligned to role profiles which includes induction training which is given to all new Members and a rolling programme of maintenance training. The Fire Authority approve a Member Development Plan each year. | YES | 2023-11-01
Cleveland FRS | Values and culture in fire and rescue services | 26899 (Rec 24) | By 1 October 2023, chief fire officers should put plans in place to monitor, including through the gathering and analysis of staff feedback, watch and team cultures and provide prompt remedial action for any issues they identify. | 2023-10-01 | A draft Staff Engagement Strategy (PPP38.1) was approved in principle by ELT January 2024. Consultation with staff and representative bodies is taking place on the strategy, which will be presented to ELT for approval March 2024. | In progress
Cleveland FRS | Values and culture in fire and rescue services | 26297 (Rec 1) | By 1 October 2023, chief fire officers should make sure their services provide a confidential way for staff to raise concerns and that staff are aware of whistleblowing processes. | 2023-10-01 | As part of our staff engagement and communications strategy, we have reviewed our mechanisms for signposting staff to our approved processes for them to raise concerns in a confidential way. The review resulted in enhancements to our existing provision which are a confidential independent reporting line (Safecall) and an easy to access internal reporting tool. These were launched across the workforce and are promoted to staff regularly through traditional methods such as news letters and notice boards as well as innovative methods such as QR codes and digital applications. CFB has well-established Whistlebowing, Grievance and Dignity at Work Policy and Procedures which have recently been reviewed to ensure that the existing and new mechanisms for raising a concern are clear. | YES | 2023-12-31
Cleveland FRS | Values and culture in fire and rescue services | 26484 (Rec 9) | By 1 January 2024, chief fire officers should: - immediately review their current background checks arrangements, and make sure that suitable and sufficient background checks are in place to safeguard their staff and communities they serve; and - make sure that appropriate DBS check requests have been submitted for all existing, new staff, and volunteers, according to their roles as identified by the Fire Standards Board. | 2024-01-01 | We undertake background checks on staff (not DBS). All new appointments undergo pre-employment background checks in line with the Government Baseline Personnel Security Standard (BPSS), this includes: • References - obtained for all employment in the previous three years. Where an individual has only had one employment in that 3-year period then a character reference will be sought. No references are accepted from relatives or friends. • Verification - this will be required in connection with issues of identity, eligibility to work as per the Asylum and Nationality Act, qualifications (where it is necessary to verify these) and other objectively justifiable requirements that the Brigade may have. An individual’s passport is required for proof of Right to Work in the UK. If they don’t have a current in date passport then we can take another combination of documents as defined under the Asylum and Nationality Act e.g. proof of NI and a Birth Certificate. All staff undertake a basic criminal records check (DBS) of unspent convictions as part of pre-employment checks, these are reviewed by the organisation and a determination of whether an applicant presents a risk will be made. Staff in roles that are not exempt from the Rehabilitation of Offenders Act e.g. those involving regulated activity undergo an Enhanced DBS check as required by their role. These enhanced DBS checks are renewed every 3 years if still required by the role. We undertake Non-Police Personnel Vetting (NPPV) level 4 and National Security Vetting (NSV) SC level as per job role requirements. In summary: • All staff – Basic DBS • Roles that are not exempt from the Rehabilitation of Offenders Act e.g., those involving regulated activity – Enhanced DBS • Flexi Duty Officers, Communications Team, Executive Leadership Team, Principal Officers, NILO’s, Group Managers and Head of I.T – NPPV Level 4 • Executive Leadership Team, Principal Officers, NILO’s, Group Managers, Head of I.T – NSV SC Level | In progress
Cleveland FRS | Values and culture in fire and rescue services | 26579 (Rec 14) | By 1 March 2024, chief fire officers should provide assurances to HMICFRS that they have implemented the standard on misconduct allegations and outcomes handling. | 2024-03-01 | Any new Fire Standard is implemented through our Internal Fire Standards Board; this is how we will capture the criteria against which we can assess our current practices to give us a gap analysis. AWAITING ISSUE OF FIRE STANARD
Cleveland FRS | Values and culture in fire and rescue services | 26532 (Rec 12) | By 1 March 2024, chief fire officers should provide assurances to HMICFRS that they have implemented the standard on staff disclosure, complaint and grievance handling. | 2024-03-01 | AWAITING ISSUE OF FIRE STANARD